## Sheet1
| Task Start from | Stage
2017-07-31 | Environment setup and install any dependancies at workstations in BriskSynergies | Detection and Retrain YOLO
2017-08-07
2017-08-14 | Look for any new car datasets that whose view points are simialr to top view
2017-08-21 | Generate new training examples from different car datasets
2017-08-28 | Re-train the YOLO with new examples
2017-09-04
2017-09-11 | Re-train the YOLO with new examples
2017-09-18
2017-09-25
2017-10-02 | Object tracking with optical flow | Tracking
2017-10-09
2017-10-16 | Object prediction using Kalman filters
2017-10-23
2017-10-30 | Solve loss of frame
2017-11-06
2017-11-13 | Solve occlusion
2017-11-20
2017-11-27
2017-12-04 | Time optimization | Time Optimization
2017-12-11
2017-12-18
2017-12-25
2018-01-01 | Generate the output format desired | Production Code Deployment
2018-01-08
2018-01-15 | Deploy YOLO on Amazon AWS
2018-01-22
2018-01-29
Note on A1: Liqiang Ding: